## Overview
KING 24x7 — Tamil News Platform
Module Priority, Progress & Risk Tracker (Spring Boot + React Build)
Prepared from: King24x7_Requirements_SpringBoot_React.docx ¦ Client reference mockup (Hostinger) ¦ Live dev build (king-tv.test-technoprint.online)
How to use this workbook
1. 'Module Tracker' — every module/feature from the client requirements doc, tagged with priority (P0-P3) and current status.
2. Where a status could be confirmed by fetching the public URLs, it is marked 'Implemented' / 'Likely Implemented' / 'Potential Gap' with the finding noted in the Evidence column.
3. Everything that sits behind login (admin dashboard, reporter workflow, ad system, SEO automation panels, etc.) is marked 'Pending Manual QA' — this environment cannot execute JavaScript or submit the admin login form, so it cannot click through an authenticated React app.
4. Use the blank 'Verified By' / 'Date' / 'Actual Status' columns on the Module Tracker sheet during a real walkthrough (log in with the credentials provided) to convert this from a requirements checklist into a true progress report.
5. 'Issues & Risks' lists concrete findings from the remote check plus structural risks called out in the requirements doc itself.
6. 'Scope Gaps & Clarifications' lists features present in the client's own reference mockup that are NOT in the written requirements doc — these need a scope decision.
7. 'Deliverables Checklist' tracks Section 6 handover items.
Snapshot (auto-calculated from Module Tracker sheet)
Metric | Count
Total tracked modules/features | 109
P0 — Critical / launch-blocking | 45
P1 — High priority | 41
P2 — Medium priority | 20
P3 — Low / post-launch | 3
Confirmed Implemented / Likely Implemented (remote check) | 3
Partially Implemented | 1
Potential Gap — Needs Verification | 3
Pending Manual QA (login-gated, not remotely verifiable) | 102
Critical risk items logged | 0
High risk items logged | 3
Key headline findings from this pass
• BRANDING MISMATCH: the client's reference site displays 'KING 24x7' with a blue theme (#0057FF); the live dev build's page title reads 'KINGS 24x7' with a brown/gold theme (#B3732A). Needs sign-off on which is correct.
• The live homepage (https://king-tv.test-technoprint.online/) returns only <head> meta tags in the raw HTML response — the <body> is empty until client-side JavaScript runs. This is consistent with a pure client-side-rendered (CSR) React SPA rather than the SSR/pre-rendering the requirements call for (§3.4, §3.7) for SEO-critical pages. This is a real risk to Google News/Discover indexing and Core Web Vitals (LCP) if not addressed before launch — flagged, not confirmed, since full rendering could not be tested.
• A Google Search Console verification meta tag IS present in both the public site and the admin portal's HTML head — a good sign that GSC setup has begun.
• The admin portal is served on a non-default, authenticated path (/admin/dashboard) rather than a predictable WordPress-style URL, matching the §3.8 requirement on that specific point.
• The shared Google Sheet link returned a 401 (access not granted to this session) and could not be read — its priorities/status could not be cross-checked into this workbook. Share it as 'Anyone with the link can view' or paste its contents if it should feed into this tracker.
• This automated pass cannot log into the admin panel or click through the authenticated React app (no JavaScript execution / form submission available in this environment), so functional correctness of reporter workflows, ad system, SEO automation, RBAC, media pipeline etc. is UNVERIFIED here and needs a manual QA pass using the credentials supplied.

## Module Tracker
Module & Feature Priority / Progress Tracker
Priority set per business criticality in the requirements doc. Status reflects what could be confirmed from public, unauthenticated URLs only (see Overview). Fill in 'Actual Status / Verified By / Date' during a live walkthrough.
Req. Ref | Module Area | Feature / Requirement | Priority | Status (Remote Check) | Evidence / Finding | Issue Identified | Actual Status (fill in after manual QA) | Verified By | Date Verified | Notes
3.1 Design & Branding
3.1 | Design & Branding | Custom brand design system (primary/secondary/accent palette) | P0 | Pending Manual QA (Not Verifiable Remotely) | Live build uses theme-color #B3732A (brown/gold); client mockup uses #0057FF (blue). | Colour palette on live build does not match client's reference mockup — needs sign-off on final brand colours.
3.1 | Design & Branding | Tamil + English dual font system (Noto Sans Tamil / Playfair or Merriweather) | P0 | Pending Manual QA (Not Verifiable Remotely) | Fonts not verifiable without rendering the page (CSR). | Confirm via manual QA / view-source of built CSS bundle.
3.1 | Design & Branding | WCAG AA colour contrast compliance | P1 | Pending Manual QA (Not Verifiable Remotely) | Requires rendered page + contrast audit tool.
3.1 | Design & Branding | Dark mode toggle, persisted per user (not just browser flag) | P2 | Pending Manual QA (Not Verifiable Remotely) | Client mockup includes a working theme/dark-mode + widget customisation panel; live build parity unconfirmed.
3.1 | Design & Branding | Fully responsive (desktop/tablet/mobile) | P0 | Pending Manual QA (Not Verifiable Remotely) | Needs manual multi-viewport QA.
3.1 | Design & Branding | Image templates: breaking news overlay, exclusive badge, sponsored label, opinion illustration | P2 | Pending Manual QA (Not Verifiable Remotely) |  | Confirm these exist as reusable design assets/components.
3.1 | Design & Branding | Custom 404 page with search bar + trending news | P2 | Pending Manual QA (Not Verifiable Remotely) | Could not be tested without triggering a real 404 route in the SPA router.
3.1 | Design & Branding | Custom maintenance page | P3 | Pending Manual QA (Not Verifiable Remotely)
3.2 Site Pages & Sections
3.2 | Homepage | Breaking news ticker | P0 | Pending Manual QA (Not Verifiable Remotely) | Present on client mockup as a scrolling ticker + price/rate widgets; live build content not visible in raw HTML (CSR).
3.2 | Homepage | Hero news grid + category tab row | P0 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Homepage | Latest news card grid, infinite scroll / load more | P0 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Homepage | Video news section | P1 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Homepage | Web stories scroll section | P1 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Homepage | Business case studies section | P1 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Homepage | Crowd reporter highlight section | P1 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Homepage | Trending sidebar | P1 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Homepage | Weather widget | P2 | Pending Manual QA (Not Verifiable Remotely) | Client mockup shows a live Chennai weather + 7-day forecast widget.
3.2 | Homepage | Newsletter signup strip | P2 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Category Pages | Filterable grid, pagination, colour coding, subcategory tabs | P0 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Article Page | Hero image, bilingual headline, byline, timestamps, reading time | P0 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Article Page | Floating social share sidebar, related articles, tags, comments, breadcrumb | P0 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Additional Pages | Video news, web stories, business case studies (sponsor badge + PDF) | P1 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Additional Pages | Crowd reporter submission page | P1 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Additional Pages | Author profile pages | P1 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Additional Pages | Search results page | P1 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Additional Pages | About / Contact / Advertise / Privacy / Terms / DMCA | P1 | Pending Manual QA (Not Verifiable Remotely)
3.2 | Additional Pages | Tag and date archives | P2 | Pending Manual QA (Not Verifiable Remotely)
3.3 News Aggregator
3.3 | Aggregator | Custom RSS/Atom ingestion service (scheduled Spring Boot job) | P1 | Pending Manual QA (Not Verifiable Remotely) | Backend scheduled job — not observable from the frontend at all. | Ask backend team directly / check server logs or admin panel for feed source config.
3.3 | Aggregator | Source name, logo, published time, external link only (no republishing) | P1 | Pending Manual QA (Not Verifiable Remotely)
3.3 | Aggregator | Noindex meta tag on all aggregated content pages | P1 | Pending Manual QA (Not Verifiable Remotely) | Cannot confirm without a live aggregated article URL.
3.3 | Aggregator | Section labelled 'From Other Sources' / 'Tamil News Digest' | P2 | Pending Manual QA (Not Verifiable Remotely)
3.4 Google News Console Integration
3.4 | Google News | Register & verify site on Google News Publisher Center | P0 | Pending Manual QA (Not Verifiable Remotely) | Cannot confirm Publisher Center status from outside Google's console. | Request screenshot/confirmation from whoever holds Publisher Center access.
3.4 | Google News | Google Search Console site verification | P0 | Likely Implemented | A 'google-site-verification' meta tag is present in both the public site and admin portal <head>.
3.4 | Google News | News XML sitemap job (Google News format, 48h refresh, last 2 days only) | P0 | Pending Manual QA (Not Verifiable Remotely) | /sitemap.xml could not be fetched by this tool (path not previously indexed/allowed); needs direct check. | Manually check https://king-tv.test-technoprint.online/sitemap.xml and the news sitemap variant.
3.4 | Google News | Content policy compliance (original reporting labels, author transparency, accurate dates) | P0 | Pending Manual QA (Not Verifiable Remotely)
3.4 | Google News | Discover eligibility (OG image sizing, AMP decision, E-E-A-T signals) | P1 | Pending Manual QA (Not Verifiable Remotely) | AMP explicitly marked 'optional / evaluate' in requirements — decision not yet made per doc. | Confirm whether AMP will be built; affects Discover eligibility plan.
3.4 | Google News | GA4 News section reporting | P1 | Pending Manual QA (Not Verifiable Remotely)
3.4 | Google News | NewsArticle schema validated via structured-data testing | P0 | Pending Manual QA (Not Verifiable Remotely) | Schema is injected server-side per spec — cannot confirm without rendered article HTML.
3.4 | Google News | Clean article URLs (no session IDs/tracking params) | P1 | Pending Manual QA (Not Verifiable Remotely)
3.5 Automated SEO Keyword System
3.5 | SEO Automation | Keyword extraction on article publish (custom / Google NL API / OpenAI / Anthropic) | P0 | Pending Manual QA (Not Verifiable Remotely) | Only testable from inside the reporter/editor publish flow.
3.5 | SEO Automation | Auto-generated SEO title, meta description, focus keyword, tags | P0 | Pending Manual QA (Not Verifiable Remotely)
3.5 | SEO Automation | Tamil Unicode keyword handling | P0 | Pending Manual QA (Not Verifiable Remotely)
3.5 | SEO Automation | Keyword density checker in editor UI | P2 | Pending Manual QA (Not Verifiable Remotely)
3.5 | SEO Automation | Internal linking automation | P2 | Pending Manual QA (Not Verifiable Remotely)
3.5 | SEO Automation | Schema generation: NewsArticle, BreadcrumbList, Organization, VideoObject, FAQPage, WebSite+SearchAction | P0 | Pending Manual QA (Not Verifiable Remotely)
3.5 | SEO Automation | Trending keyword dashboard (admin) | P2 | Pending Manual QA (Not Verifiable Remotely)
3.5 | SEO Automation | XML sitemaps: news, video, image, standard — submitted to GSC + Bing | P0 | Pending Manual QA (Not Verifiable Remotely) | Not directly checkable by this tool; verify manually.
3.5 | SEO Automation | Meta title/description length, OG + Twitter cards, canonical, hreflang (ta/en) | P0 | Partially Implemented | Homepage <head> has title, meta description, viewport, theme-color; OG/Twitter/canonical/hreflang not confirmed and not present on the fetched homepage response. | Homepage is missing an og:title/og:description/canonical tag in the raw HTML response captured — confirm whether these are injected only client-side (which would defeat their SEO purpose) or via SSR.
3.5 | SEO Automation | Core Web Vitals: LCP<2.5s, CLS<0.1, INP<200ms, PSI 90+ mobile | P0 | Potential Gap - Needs Verification | Raw HTML response has an empty <body> until JS executes — classic CSR pattern, which historically hurts LCP and PSI mobile scores unless heavily optimised. | Run an actual PageSpeed Insights test against the live URL before relying on this column further.
3.6 S3-Compatible Cloud Media Storage
3.6 | Media Storage | Custom Media Service (AWS SDK / S3-compatible SDK), no plugin dependency | P0 | Pending Manual QA (Not Verifiable Remotely) | Backend implementation, not visible from outside.
3.6 | Media Storage | All media types offloaded (image/video/audio/docs/web story assets) | P0 | Pending Manual QA (Not Verifiable Remotely)
3.6 | Media Storage | CDN delivery via Cloudflare / CloudFront | P0 | Pending Manual QA (Not Verifiable Remotely)
3.6 | Media Storage | Media URLs auto-rewritten to CDN URL | P1 | Pending Manual QA (Not Verifiable Remotely)
3.6 | Media Storage | No local disk retention after successful S3 upload | P1 | Pending Manual QA (Not Verifiable Remotely)
3.6 | Media Storage | Direct video upload to S3 + transcoding pipeline (1080p/720p/480p) | P1 | Pending Manual QA (Not Verifiable Remotely)
3.6 | Media Storage | HLS adaptive streaming for mobile | P2 | Pending Manual QA (Not Verifiable Remotely)
3.6 | Media Storage | Bucket organisation convention (/images/yyyy/mm/ etc.) | P1 | Pending Manual QA (Not Verifiable Remotely)
3.6 | Media Storage | Access control — public-read delivery, write via backend service creds only | P0 | Pending Manual QA (Not Verifiable Remotely)
3.6 | Media Storage | Bucket versioning + lifecycle policy (cold storage >1yr) | P1 | Pending Manual QA (Not Verifiable Remotely)
3.6 | Media Storage | Storage cost monitoring/alerting | P2 | Pending Manual QA (Not Verifiable Remotely)
3.7 Performance Optimization
3.7 | Performance | React/Vite component library; SSR or pre-rendering for SEO-critical pages | P0 | Potential Gap - Needs Verification | Homepage HTML returned with an empty body and only <head> tags — indicates the page is not server-rendered/pre-rendered as delivered to this fetch, which is exactly the mechanism the requirement calls for on SEO-critical pages. | Confirm with the dev team whether SSR/pre-render is implemented but blocked for bots/tools, or genuinely not yet built.
3.7 | Performance | Redis-based response caching for list/search endpoints | P1 | Pending Manual QA (Not Verifiable Remotely) | Backend-only, not observable remotely.
3.7 | Performance | Vite build minification & code-splitting | P1 | Pending Manual QA (Not Verifiable Remotely)
3.7 | Performance | Custom image-processing pipeline (compression, WebP) | P0 | Pending Manual QA (Not Verifiable Remotely)
3.7 | Performance | Cloudflare CDN/DNS layer | P1 | Pending Manual QA (Not Verifiable Remotely)
3.7 | Performance | Google Fonts hosted locally | P2 | Pending Manual QA (Not Verifiable Remotely)
3.7 | Performance | Infinite scroll / load-more on feeds | P2 | Pending Manual QA (Not Verifiable Remotely)
3.7 | Performance | Scheduled DB maintenance jobs | P2 | Pending Manual QA (Not Verifiable Remotely)
3.7 | Performance | Tree-shaking / dead code elimination at build time | P1 | Pending Manual QA (Not Verifiable Remotely)
3.7 | Performance | Responsive srcset on all images | P1 | Pending Manual QA (Not Verifiable Remotely)
3.8 Security Configuration
3.8 | Security | Spring Security auth/RBAC + rate limiting + Cloudflare WAF | P0 | Pending Manual QA (Not Verifiable Remotely)
3.8 | Security | Two-factor authentication (TOTP) for editor/admin accounts | P0 | Pending Manual QA (Not Verifiable Remotely) | Not tested — would require an actual admin login attempt.
3.8 | Security | Login attempt limit (3 attempts -> IP block) | P0 | Pending Manual QA (Not Verifiable Remotely) | Not safe to brute-force test in this pass.
3.8 | Security | Admin panel on non-predictable route, gated by authenticated API | P1 | Likely Implemented | Admin portal is served at /admin/dashboard (not a default CMS path) and returns a distinct 'KING24X7 — Admin Portal' shell rather than site content — consistent with a gated SPA route.
3.8 | Security | Web Application Firewall active (Cloudflare or equivalent) | P0 | Pending Manual QA (Not Verifiable Remotely) | WAF headers/behaviour not distinguishable from a simple GET request.
3.8 | Security | Daily automated DB + media backups | P0 | Pending Manual QA (Not Verifiable Remotely)
3.8 | Security | SSL certificate active, HTTPS enforced sitewide | P0 | Implemented | Both the public site and admin portal load successfully over HTTPS.
3.8 | Security | Secrets managed via env vars / secrets manager (never in source control) | P0 | Pending Manual QA (Not Verifiable Remotely) | Requires source/repo access to confirm, not a live-site check.
3.8 | Security | Security headers (X-Frame-Options, X-Content-Type-Options, Referrer-Policy, Permissions-Policy, CSP) | P0 | Pending Manual QA (Not Verifiable Remotely) | Response headers were not captured in this pass — recommend a manual `curl -I` / browser devtools check. | Run a header scan (e.g. securityheaders.com) against the live URL.
3.8 | Security | UptimeRobot monitoring, 1-min downtime alert | P1 | Pending Manual QA (Not Verifiable Remotely)
3.9 Advertising System
3.9 | Advertising | Custom Ad Management module (React admin UI + Spring Boot backend) | P1 | Pending Manual QA (Not Verifiable Remotely)
3.9 | Advertising | 10 required ad placements (leaderboard, mobile sticky, sidebar rectangle, in-content x2, sticky sidebar, interstitial, video pre-roll, sponsored card, footer banner, newsletter slot) | P1 | Pending Manual QA (Not Verifiable Remotely) | Not visible without rendering the live pages; no ad units were observable in the raw HTML fetch of the homepage (expected, since body is empty pre-JS).
3.9 | Advertising | Geo/device targeting, rotation, frequency capping, impression/click tracking, expiry | P1 | Pending Manual QA (Not Verifiable Remotely)
3.9 | Advertising | Slot layout ready for future AdSense programmatic fill | P2 | Pending Manual QA (Not Verifiable Remotely)
3.10 Reporter & Crowd Sourcing Workflow
3.10 | Reporter Workflow | 7-role RBAC (Subscriber, Crowd Reporter, Staff Reporter, Sub Editor, Section Editor, Chief Editor, Administrator) | P0 | Pending Manual QA (Not Verifiable Remotely)
3.10 | Reporter Workflow | Reconcile 7-role CMS model with existing King24x7 platform roles (Super Admin/Chief Editor/District Admin/Mobile Journalist/Institution Login/Public) | P0 | Pending Manual QA (Not Verifiable Remotely) | The requirements doc itself flags this as an open decision, not yet resolved. | OPEN DECISION — the requirements doc explicitly calls this out as unresolved and blocking backend RBAC implementation. Needs a client/product decision before this can be marked complete.
3.10 | Reporter Workflow | Editorial calendar module (React admin UI + scheduling API) | P1 | Pending Manual QA (Not Verifiable Remotely)
3.10 | Reporter Workflow | Reporter dashboard scoped to own drafts/published count | P1 | Pending Manual QA (Not Verifiable Remotely)
3.10 | Reporter Workflow | Crowd reporter submission form (name/location, title, text, image, video link) | P1 | Pending Manual QA (Not Verifiable Remotely)
3.10 | Reporter Workflow | Auto email notification to sub-editor on new crowd submission | P1 | Pending Manual QA (Not Verifiable Remotely)
3.11 Additional Features
3.11 | Additional | Breaking news alert bar (dismissible) | P1 | Pending Manual QA (Not Verifiable Remotely) | Present as a ticker in the client mockup.
3.11 | Additional | OneSignal push notifications (free plan) | P2 | Pending Manual QA (Not Verifiable Remotely)
3.11 | Additional | WhatsApp share button on article pages | P1 | Pending Manual QA (Not Verifiable Remotely)
3.11 | Additional | Telegram auto-post via bot integration | P2 | Pending Manual QA (Not Verifiable Remotely)
3.11 | Additional | AMP for articles — status: optional, needs evaluation per requirements doc | P3 | Pending Manual QA (Not Verifiable Remotely) | Requirements doc marks this as a decision point, not a firm requirement. | Decide AMP vs. SSR-only approach; document the decision.
3.11 | Additional | Reading progress bar on article pages | P3 | Pending Manual QA (Not Verifiable Remotely)
3.11 | Additional | Estimated reading time on cards + articles | P2 | Pending Manual QA (Not Verifiable Remotely)
3.11 | Additional | Related articles by category/tag (not random) | P1 | Pending Manual QA (Not Verifiable Remotely)
3.11 | Additional | Tamil-aware search (Elasticsearch/OpenSearch with Tamil analyzer) | P0 | Pending Manual QA (Not Verifiable Remotely)
3.11 | Additional | Bilingual content model (DB-level TA/EN fields) + language toggle | P0 | Pending Manual QA (Not Verifiable Remotely)
3.11 | Additional | Author archive + tag archive pages with SEO meta | P2 | Pending Manual QA (Not Verifiable Remotely)
Section 4 — Technical Foundation
4 | Technical | Frontend: React + Vite, SSR/pre-rendering evaluated for SEO pages | P0 | Potential Gap - Needs Verification | Same CSR-only observation as §3.7 above.
4 | Technical | Backend: Java Spring Boot, versioned REST API (/api/v1/...) | P0 | Pending Manual QA (Not Verifiable Remotely)
4 | Technical | Database: MySQL/TiDB or PostgreSQL, supports geo/radius + full-text queries | P0 | Pending Manual QA (Not Verifiable Remotely)
4 | Technical | JWT auth with refresh-token rotation + RBAC | P0 | Pending Manual QA (Not Verifiable Remotely)
4 | Technical | S3-compatible object storage via custom Media Service | P0 | Pending Manual QA (Not Verifiable Remotely)
4 | Technical | Hosting: AWS/GCP, auto-scaling app tier, managed DB, CDN | P0 | Pending Manual QA (Not Verifiable Remotely)
4 | Technical | Full API docs, DB schema docs, deployment runbook | P1 | Pending Manual QA (Not Verifiable Remotely)
4 | Technical | Passes Google Mobile Usability Test | P1 | Pending Manual QA (Not Verifiable Remotely) | Requires Google Search Console mobile usability report access.

## Issues & Risks
Issues & Risk Register
Findings from the remote check of the live build, plus structural risks called out in the requirements document itself.
# | Category | Finding / Risk | Potential Impact | Likelihood | Risk Level | Recommended Action
1 | Branding / Design | Live dev build shows page title 'KINGS 24x7' and a brown/gold theme (#B3732A); client's own reference mockup shows 'KING 24x7' with a blue theme (#0057FF). | Brand inconsistency at launch; possible rework of colour tokens/logo across the whole component library if the wrong direction was built. | Confirmed (observed directly) | Medium | Get written sign-off from the client on the exact brand name spelling and colour palette before more UI is built on the current theme.
2 | SEO / Rendering Architecture | The live homepage's raw HTML response contains only <head> tags — the <body> is empty until client-side JavaScript executes (classic CSR SPA pattern). | Requirements (§3.4, §3.7) call for SSR/pre-rendering on SEO-critical pages specifically to satisfy Google News/Discover indexing and Core Web Vitals (LCP). A CSR-only build risks poor crawlability and slow LCP scores. | Observed on 1 URL; not yet confirmed at scale | High | Have the dev team confirm SSR/pre-rendering status directly, then validate with Google's Mobile-Friendly/Rich Results tests and a real PageSpeed Insights run before sign-off.
3 | SEO / Meta Tags | No Open Graph, Twitter Card, canonical, or hreflang tags were present in the raw HTML head of the homepage fetch — only title, meta description, viewport and theme-color were found. | If these are only injected client-side, social sharing previews and canonical/duplicate-content signals may not be picked up correctly by crawlers and social platforms that don't execute JS. | Observed on 1 URL | Medium | Verify whether OG/canonical/hreflang tags are server-rendered; test with Facebook Sharing Debugger and a raw curl request.
4 | Governance / Access | The shared Google Sheet (requirements/status tracker) returned a 401 — this session has no read access to it. | Any priorities, deadlines, or status already tracked by the client in that sheet could not be cross-checked or merged into this workbook, risking two conflicting sources of truth. | Confirmed (access denied) | Medium | Share the sheet as 'Anyone with the link – Viewer', or export/paste its contents so it can be reconciled with this tracker.
5 | Role Model / RBAC | The requirements document itself flags that the 7-role CMS model (§3.10) has not yet been reconciled with the existing King24x7 platform's role hierarchy (Super Admin/Chief Editor/District Admin/Mobile Journalist/Institution Login/Public). | Backend RBAC, permission tables and reporter dashboards may need rework if this decision is made after implementation starts. | Confirmed (stated in requirements doc) | High | Escalate as a blocking decision — get client/product sign-off on the unified role model before further backend RBAC work.
6 | Scope / AMP | AMP support for articles is marked 'optional — evaluate' in the requirements rather than a firm yes/no. | Ambiguity could lead to late discovery that Google Discover eligibility assumptions don't hold without AMP, or wasted effort building AMP that isn't needed. | Confirmed (stated in requirements doc) | Medium | Make an explicit AMP go/no-go decision early, backed by a Core Web Vitals test on the SSR/pre-rendered build.
7 | Scope Creep | The client's own reference mockup includes many rich features not described anywhere in the written requirements document (see 'Scope Gaps & Clarifications' sheet) — commodity/stock/crypto price tickers, dam water-level widgets, an election results centre, daily polls, obituary/wishes/classifieds/jobs sections, and a live widget-customisation panel. | If these are expected at launch but were never quoted/scoped, they represent significant unbudgeted and untimelined work. | Confirmed (observed in mockup) | High | Walk through the mockup with the client feature-by-feature and get an explicit in/out-of-scope decision on each item, then update the SOW/timeline/budget accordingly.
8 | Verification Coverage | This automated pass cannot execute JavaScript or submit the admin login form, so ~90% of the functional requirements (reporter workflow, ad system, SEO automation, media pipeline, RBAC, security controls) could not be verified and are marked 'Pending Manual QA'. | Without a manual walkthrough, the actual completion percentage of the build is unknown — this workbook is a checklist/framework, not a verified progress report. | N/A — a scope limitation of this check, not a defect in the build | Medium | Have someone log in with the provided admin credentials and a reporter account, and walk each 'Pending Manual QA' row in the Module Tracker, filling in the 'Actual Status' column.
9 | SEO / Sitemaps | Google News XML sitemap, video sitemap, image sitemap and standard sitemap could not be independently fetched/verified in this pass. | If sitemaps are missing or malformed, Google News Publisher Center submission and article indexing will be blocked. | Unverified | Medium | Manually check /sitemap.xml and the news-sitemap endpoint on the live domain and validate against Google's news sitemap spec.
10 | Security Headers | HTTP response security headers (CSP, X-Frame-Options, Referrer-Policy, Permissions-Policy, X-Content-Type-Options) were not captured in this pass. | Missing headers are a common launch-blocking security gap for news sites (clickjacking, MIME sniffing, XSS surface). | Unverified | Medium | Run a header scan (e.g. securityheaders.com) against the live production-candidate URL before go-live.

## Scope Gaps & Clarifications
Scope Gaps & Clarifications Needed
Features visible in the client's own reference mockup (lightcoral-sparrow-608215.hostingersite.com) that are NOT described anywhere in King24x7_Requirements_SpringBoot_React.docx. Each needs an explicit in/out-of-scope decision.
# | Feature seen in client mockup | Description | In written requirements doc? | Suggested next step
1 | Gold/silver/platinum price ticker | Live per-gram rates for Chennai gold, silver, platinum. | Not mentioned | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.
2 | Vegetable & commodity price board | Daily prices for tomato, onion, potato, coconut, garlic etc. | Not mentioned | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.
3 | Agri commodity price board | Paddy, cotton, turmeric, groundnut, sugarcane prices. | Not mentioned | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.
4 | Fuel price ticker | Petrol/diesel/LPG/CNG prices for Chennai. | Not mentioned | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.
5 | Stock market ticker | Sensex, Nifty, Bank Nifty, gold futures, crude oil. | Not mentioned | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.
6 | Cryptocurrency ticker | Bitcoin, Ethereum, Solana, XRP prices. | Not mentioned | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.
7 | Dam / reservoir water-level widgets | Current level, capacity, inflow/outflow for 7 named dams. | Not mentioned | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.
8 | Election Centre 2026 | Live seat count and vote-share by party. | Not mentioned | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.
9 | Daily reader poll | 'Who will be the next CM?' style live poll with results. | Not mentioned | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.
10 | Live TV module | Embedded live broadcast + schedule of today's programmes. | Only 'YouTube channel network' mentioned — a dedicated Live TV player/schedule module is not described. | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.
11 | Reader-submitted local posts ('வாசகர் பக்கம்') | Community members post local items directly (distinct from the Crowd Reporter news-submission flow in §3.10). | Not mentioned as a separate module — may overlap with crowd reporter workflow; needs reconciling. | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.
12 | Local community modules | Directory ('நம்ம ஊர்'), Wishes ('வாழ்த்து'), Obituaries ('இரங்கல்'), Classifieds ('தள்ளுபடி'), Jobs ('வேலை'), Buy/Sell. | Not mentioned anywhere in the RFP scope of work. | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.
13 | Widget customisation panel | End-user controls for theme, accent colour, font size, and show/hide of individual homepage widgets. | Dark mode toggle is required (§3.1); the broader widget-level customisation panel is not. | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.
14 | District-wise city selector in header | Quick-switch between 10 named Tamil Nadu cities for localised content. | Not explicitly described — 'District news' pages are mentioned generically in §3.2/§3.10 role table (District Admin) but not this specific header UI. | Confirm with client whether this is in scope for this phase; if yes, add to Module Tracker with a priority and owner.

## Deliverables Checklist
Handover Deliverables Checklist (Section 6 of Requirements)
# | Deliverable | Status | Notes
1 | Complete Spring Boot backend + React frontend application, deployed, source code handed over via Git repository | Pending Manual QA (Not Verifiable Remotely)
2 | Brand style guide document — colour codes, fonts, spacing standards | Pending Manual QA (Not Verifiable Remotely)
3 | Third-party service/API list (payment gateway, SMS/OTP, AI provider, maps/geocoding, CDN, hosting) with licence/subscription and renewal details | Pending Manual QA (Not Verifiable Remotely)
4 | S3 storage configuration report — bucket structure, access policy, CDN setup | Pending Manual QA (Not Verifiable Remotely)
5 | Google News Publisher Center submission confirmation | Pending Manual QA (Not Verifiable Remotely)
6 | SEO automation configuration report — keyword extraction, schema, sitemaps | Pending Manual QA (Not Verifiable Remotely)
7 | Security configuration report confirming all measures active | Pending Manual QA (Not Verifiable Remotely)
8 | PageSpeed Insights screenshots confirming 90+ mobile score | Pending Manual QA (Not Verifiable Remotely)
9 | Google Search Console and GA4 fully connected and verified | Pending Manual QA (Not Verifiable Remotely)
10 | Admin training session — minimum 2 hours for editorial team | Pending Manual QA (Not Verifiable Remotely)
11 | Reporter role training guide (PDF) | Pending Manual QA (Not Verifiable Remotely)
12 | All source code, design files, login credentials, API documentation, and database schema documentation handed over to client | Pending Manual QA (Not Verifiable Remotely)